## Project Plan
BHUTAN TELECOM LIMITED |  |  |  | PROJECT PLAN
PROJECT - Rescue 1.0
Drafted on 29/04/2016 at 7:20pm
| Sl# | Item |  | (29th April, 2016 - 29th May, 2016) |  |  |  | (30th May, 2016 - 29th June, 2016) |  |  |  | (30th June, 2016 - 29th July, 2016)
|  |  |  | w1 (6th May) | w2 (13th May) | w3 (20th May) | w4 (27th May) | w5 (6th Jun) | w6 (13th Jun) | w7 (20th Jun) | w8 (27th Jun) | w9 (6th Jul) | w10 (13th Jul) | w11 (20th Jul) | w12 (27th Jul)
| 1 | Environment Setup
i) Data Base Setup (MariaDB)
ii) Network Connectivity
iii) FTP Automation
iv) GUI (HTML, CSS, JS, PHP)
| 2 | Develop Parser to parse the NEs
i) SoftSwitch
ii) MSC
iii) SGSN
iv) GGSN
v) SMSC
vi) PRBT
| 3 | Load the Parsed files into Reporting Server
i) SoftSwitch (NA)
ii) MSC (SIEMENS)
iii) SGSN (SIEMENS)
iv) GGSN (SIEMENS)
v) SMSC
vi) PRBT
| 4 | Load the Stats from BS
i) SoftSwitch (TIIMS)
ii) MSC (E///)
iii) SGSN (E///)
iv) GGSN (E///)
v) SMSC
vi) PRBT
| 5 | Reconcile
i) Reconcile CDRs
ii) Reconcile UDRs
iii) Reconcile Charges

## Version
29/04/2016 | Version | 1.0 | Original

## Working Hours
1) | 2 hours every day from 5:30pm - 7:30pm
2) | Every Sunday From 12pm - 6pm
3)

## Project Members
1 | Dorji
2 | Gopal
3 | Phuntsho Gayenden
4 | Shiv
5 | Yeshi